\*\*\*\*\*Please note that these timelines could be subject to change depending on further announcements from HUD.

Current Online Resources released by HUD are as follows:

[FY 2016 Continuum of Care (CoC) Program Competition: Funding Availability](https://www.hudexchange.info/e-snaps/fy-2016-coc-program-nofa-coc-program-competition/)

The local process is administered by the staff of the Continuum of Care (CoC) lead for Nashville, Davidson County, TN (TN-504), and the Metropolitan Development & Housing Agency (MDHA).

Please Note: The CoC Lead and Homeless Management Information System (HMIS) lead staff administer this competitive process only. Staff does not hold a vote on any of the decision-making bodies involved in this competitive process itself. Staff Includes:

Suzie Tolmie: CoC Homeless Coordinator

Mandy Wood: HMIS Systems Administrator

Please notice the difference in due dates between renewal projects applications and new project applications.

|  |
| --- |
| **[TN: 504 Events & Schedule for fy2016 national competition]** |

|  |  |  |
| --- | --- | --- |
| **Nashville, TN: FY2016 Timeline** | **Key Dates:** | **Actions Need from Agencies:** |
| Open meeting on **Reallocation** with CoC Providers (discussion on MDHA unexpended funds lost in FY2015 included) | **06.30.2016** | ***Completed on Time*** |
| Open meeting for FY2015 CA Review Community Workshop to review narrative and priority listing | **07.11.2016** | ***Completed on Time*** |
| July 2016 CoC General Meeting | **07.21.2016** | ***Completed On Time*** |
| FY2016 CoC Applications for Renewal Projects | **08.05.2016 by 12:00 pm**  | ***Completed on Time: (16) Submissions*** |
| MDHA to Staff PEC Orientation for current and new members | **08.09.2016** | ***Completed On Time: 5 New Members*** |
| Renewal Applications Scored by MDHA Staff and forwarded to PEC *(MDHA Grants will be scored independently by a PEC Member)* | **08.10.2016** | ***Completed On Time*** |
| FY2016 CoC Applications for New Projects | **08.12.2016 by 4:00 pm** | ***Completed on Time: (6) Submissions for new via Reallocation or Bonus*** |
| FY2016: 30 Day Project Application Deadline for Local Consideration (HUD Required) | **08.14.2016** | ***Completed On Time: All projects considered*** |
| August-CoC Governance Board Meeting | **08.16.2016** | ***Completed On Time*** |
| New Applications Scored and forwarded to PEC | **08.17.2016** | **None** |
| August 2016 CoC General Meeting | **08.18.2016** | **None** |
| **PEC Committee Will Review Scores for both renewal and new** | **08.23.2016**  | ***Completed On Time: Scenario Finalized by PEC*** |
| SPECIAL CALLED GOVERNANCE MEETING  | **08.26.2016** | **NEW EVENT ADDED: Scenario accepted by Governance** |
| Notice of Project Acceptance or Rejection from locally (HUD Required) | **08.31.2016 (This is not the same as ranking and prioritizing! This is just a notification that the project is or is not accepted by CoC.)** |
| Any appeals regarding ranking or scoring must be submitted (Must cite one of the reasons listed in the Appeals Overview document to be considered) | **09.06.2016-09.07.2016** | **Date Changed: Appeals Given until September 7th, 2016 at 5:00 pm for last call filings** |
| SPECIAL CALLED GOVERNANCE and CoC General Body Membership | **09.07.2016** | **NEW EVENT ADDED: Tier II Ranking and Appeals** |
| Appeals Committee (Non Designated PEC Members) will review appeal motion/ & provide to agency | **09.08.2016** | **Date Changed: Appeals Teleconference** |
| FY2016 Collaborative Application & Priority Ranking Posted (48) Hours in Advance of Deadline from HUD | **09.09.2016** | **NEW EVENT ADDED** |
| Collaborative Application for Nashville, TN | **September 14th, 2016** | **None-Will post public screenshot and final Application** |